# Implementatieplan: llm-eval CLI

Versie: 1.0

Datum: 20 december 2025

Gebaseerd op: ADR-001 v2.0 Geconsolideerd, RFC-001 Packaging

Sprint cadence: Wekelijkse releases, tweewekelijkse sprint planning

# 1. Executive Summary

Dit plan beschrijft de eerste 8 weken van ontwikkeling voor de llm-eval CLI. We leveren een werkende MVP in week 6 (v0.2.0) met deterministische metrics, gevolgd door LLM-as-judge capabilities in week 8 (v0.3.0).

| Week | Release | Milestone |
| --- | --- | --- |
| 2 | v0.0.1 | Internal: CLI skeleton + config parsing werkt |
| 4 | v0.1.0 | Public alpha: Baseline management + JUnit output |
| 6 | v0.2.0 | MVP: Deterministische metrics + SARIF + GitHub Action |
| 8 | v0.3.0 | LLM-as-judge + FP tracking dashboard |

# 2. Team Allocatie per Week

| Week | Tech Lead | SDK/DX | Evals Lead | DevRel |
| --- | --- | --- | --- | --- |
| 1 | Cargo workspace | Package claims | ADR-002 draft | Partners |
| 2 | Config + SQLite | CI/CD + musl | Golden schema | Naming |
| 3 | Test runner | Error messages | Example suite | Docs v1 |
| 4 | Baselines | v0.1.0 release | Partner tests | Launch |
| 5 | JSON Schema | Embedding SDK | Semantic sim | Feedback |
| 6 | SARIF output | GH Action | Thresholds | v0.2.0 |
| 7 | LLM client | Multi-sample | Faithfulness | Blog |
| 8 | FP tracking | Dispute btn | Calibratie | v0.3.0 |

# 3. Gedetailleerde Weekplannen

## Week 1: Foundation & Claims

Doel: Project structuur staat, alle externe dependencies geclaimd

### Tech Lead: Cargo Workspace Setup

- Task 1.1: cargo init met workspace layout

Structuur: llm-eval-core (lib), llm-eval-cli (bin), llm-eval-metrics (lib)

- Task 1.2: Clap v4.5 subcommand skeleton

Commands: eval run, eval ci, eval init, eval baseline, eval compare, eval version

- Task 1.3: Basis dependencies toevoegen

tokio, serde, serde_yaml, rusqlite, anyhow, thiserror

Acceptance criteria:

- cargo build --release compileert zonder warnings

- ./target/release/llm-eval --help toont alle subcommands

- Exit code 0 voor --help, exit code 2 voor unknown commands

### SDK/DX Engineer: Package Name Claims

- Task 1.4: Claim llm-eval op PyPI (placeholder package)

- Task 1.5: Claim llm-eval op npm (placeholder)

- Task 1.6: Reserve crates.io name

- Task 1.7: Setup homebrew-llm-eval tap repository

### Evals Lead: ADR-002 Draft

- Task 1.8: ADR-002 eerste draft: Metrics Engine architectuur

- Task 1.9: Prompt templates voor LLM-as-judge (Faithfulness, Answer Relevancy)

### Product/DevRel: Design Partners

- Task 1.10: Identificeer 3-5 RAG teams als design partners

- Task 1.11: Eerste intake gesprekken: wat is hun grootste pijn?

## Week 2: Config & CI/CD

Doel: YAML config parsing werkt, release pipeline staat, v0.0.1 internal build

### Tech Lead: Config & Storage

- Task 2.1: YAML config parser met serde_yaml

eval.yaml schema: suite, model, tests[], version (verplicht)

- Task 2.2: SQLite schema voor test results + baselines

Tables: runs, test_cases, results, baselines, cache

- Task 2.3: Config version validation + migration error handling

Acceptance criteria:

- eval init genereert een valide eval.yaml met version: 1

- eval run met incomplete config geeft actionable error message

### SDK/DX Engineer: Release Pipeline

- Task 2.4: GitHub Actions workflow met cargo-dist

- Task 2.5: Build matrix: linux-x64, linux-arm64, linux-musl, darwin-x64, darwin-arm64, windows-x64

- Task 2.6: TestPyPI + npm dry-run release

Acceptance criteria:

- Tag push triggert automatische build voor alle 6 platforms

### Evals Lead: Golden Dataset Schema

- Task 2.7: Finaliseer YAML schema voor test cases

- Task 2.8: Maak 10 example test cases voor RAG scenario

## Week 3: Test Runner Engine

Doel: Parallel test execution werkt, VCR record/replay functioneel

### Tech Lead: Async Test Runner

- Task 3.1: Tokio-based test runner met concurrency control

--parallel N flag, default: num_cpus

- Task 3.2: LLM client abstraction trait

trait LlmClient { async fn complete(&self, prompt: &str) -> Result<Response> }

- Task 3.3: VCR record/replay voor LLM calls

Content-addressable cache: hash(model + prompt + config) → response

Acceptance criteria:

- Tweede run van zelfde tests is 10x sneller (cached)

- --refresh-cache forceert nieuwe API calls

### SDK/DX Engineer: Error Message Refinement

- Task 3.4: RFC-002 Error Message Style Guide

- Task 3.5: Implementeer contextual hints voor top-10 error scenarios

## Week 4: Baselines & v0.1.0

Doel: v0.1.0 public alpha release

### Tech Lead: Baseline Management

- Task 4.1: eval baseline save command

- Task 4.2: eval compare met delta reporting

- Task 4.3: JUnit XML output generator

Acceptance criteria:

- JUnit XML parseert correct in Jenkins/GitHub Actions test summary

### SDK/DX Engineer: v0.1.0 Release

- Task 4.4: Release naar PyPI, npm, crates.io, Homebrew tap

- Task 4.5: Verify install op verse machines (CI matrix)

- Task 4.6: Troubleshooting docs voor common install issues

### Product/DevRel: Alpha Launch

- Task 4.7: README met quickstart (install → init → run in <5 min)

- Task 4.8: Share met design partners, verzamel eerste feedback

## Week 5: Deterministische Metrics

Doel: JSON Schema validation + Semantic Similarity werken

### Tech Lead: JSON Schema Metric

- Task 5.1: JSON Schema validation met jsonschema crate

- Task 5.2: Actionable error output bij schema violations

Acceptance criteria:

- Schema violation toont exact welk veld faalt en waarom

### Evals Lead: Semantic Similarity

- Task 5.3: Embedding provider abstraction (OpenAI ada-002, local sentence-transformers)

- Task 5.4: Cosine similarity metric implementatie

- Task 5.5: Threshold configuratie (default: 0.85)

## Week 6: SARIF & v0.2.0 MVP

Doel: v0.2.0 MVP release met GitHub Action

### Tech Lead: SARIF Output

- Task 6.1: SARIF 2.1.0 output generator

- Task 6.2: Map test failures naar code locations (indien beschikbaar)

### SDK/DX Engineer: GitHub Action

- Task 6.3: GitHub Action: llm-eval/action@v1

- Task 6.4: SARIF upload naar GitHub Code Scanning

- Task 6.5: Marketplace listing

### Evals Lead: Threshold System

- Task 6.6: Relatieve threshold implementatie (5% regressie default)

- Task 6.7: Absolute floor guardrail (min_score: 0.5)

## Week 7-8: LLM-as-Judge (Fast Follow)

Doel: v0.3.0 met LLM-as-judge + FP tracking

### Week 7: LLM-as-Judge Implementation

- Task 7.1: Multi-provider LLM client (OpenAI, Anthropic)

- Task 7.2: Multi-sample voting (3 samples, majority vote)

- Task 7.3: Early-exit optimization (2 unanimous → skip 3rd)

- Task 7.4: Faithfulness metric (RAG context verification)

- Task 7.5: Answer Relevancy metric

### Week 8: FP Tracking & v0.3.0

- Task 8.1: Vote-spread transparantie ('Passed 3/3' vs 'Passed 2/3')

- Task 8.2: 'Unstable' status voor 2-1 votes (SARIF warning, niet failure)

- Task 8.3: Dispute button voor design partners

- Task 8.4: FP tracking dashboard (simpele HTML report)

- Task 8.5: v0.3.0 release

# 4. Technische Specificaties

## 4.1 Repository Structuur

llm-eval/
├── Cargo.toml                 # Workspace root
├── crates/
│   ├── llm-eval-core/         # Shared types, config, storage
│   ├── llm-eval-cli/          # Binary, clap commands
│   └── llm-eval-metrics/      # Metric implementations
├── .github/
│   ├── workflows/
│   │   ├── ci.yml             # PR checks
│   │   └── release.yml        # cargo-dist
│   └── actions/
│       └── llm-eval/          # GitHub Action
├── packages/
│   ├── python/                # PyPI wheel build
│   └── npm/                   # npm postinstall wrapper
├── docs/
│   ├── quickstart.md
│   └── config-reference.md
└── examples/
    ├── rag-basic/
    └── structured-output/

## 4.2 Config Schema (v1)

# eval.yaml
version: 1                    # Required, enables migrations
suite: my-rag-tests
model: gpt-4o
settings:
  parallel: 4
  timeout_seconds: 30
  cache: true
thresholds:
  regression_percent: 5       # Fail if >5% worse than baseline
  min_score: 0.5              # Absolute floor
tests:
  - id: factual-qa-001
    input:
      prompt: "What is the capital of France?"
      context:                # Optional, for RAG
        - "Paris is the capital of France."
    expected:
      must_contain: ["Paris"]
      json_schema: null       # Or path to schema
    tags: [factual, geography]

## 4.3 Exit Codes

| Code | Meaning | CI Behavior |
| --- | --- | --- |
| 0 | All tests passed | Continue pipeline |
| 1 | One or more tests failed | Block merge, show failures |
| 2 | Configuration or setup error | Show error, user action required |
| 3 | Unstable results (LLM-judge disagreement) | Warning, configurable block |

# 5. Risico Register

| Risico | Week | Mitigatie |
| --- | --- | --- |
| Package name conflict | 1 | Claim in eerste dagen; backup: 'evalgate' of 'llm-probe' |
| cargo-dist edge cases | 2 | Fallback naar handmatige workflow; test early |
| Design partner no-show | 1-4 | 5 partners, 3 committed = voldoende |
| LLM API rate limits | 3-4 | VCR caching; configurable batch size |
| SARIF spec complexity | 6 | Use existing sarif crate; minimal viable output first |
| LLM-judge instability | 7-8 | Multi-sample voting; 'unstable' status vs hard fail |

# 6. Definition of Done

Elke taak is 'done' als:

- Code gemerged naar main met passing CI

- Unit tests dekken happy path + belangrijkste error cases

- Acceptance criteria uit dit document gevalideerd

- Documentatie bijgewerkt (README, inline docs)

- Geen bekende regressies in bestaande functionaliteit

Elke release is 'done' als:

- Alle milestone taken voor die week zijn done

- Install getest op verse machines (Linux, macOS, Windows)

- Design partner kan quickstart volgen zonder hulp

- Changelog en release notes gepubliceerd

# 7. Communicatie & Ritme

| Activiteit | Frequentie & Format |
| --- | --- |
| Daily standup | Async Slack: what I did, what I'll do, blockers |
| Weekly release | Vrijdag: tag, build, deploy, changelog update |
| Sprint planning | Elke 2 weken maandag: review vorige sprint, plan volgende |
| Design partner sync | Weekly 30min met 1 partner: live demo, feedback verzamelen |
| Technical deep-dive | Ad-hoc: als architectuurvragen opkomen, document als ADR |

───────────────────────────────────────────

Dit implementatieplan is goedgekeurd. Eerste sprint start maandag.

Eerste actie vandaag: cargo init llm-eval